## Slide 1
ELS Get Well Plan
Experimental Licensing System · OET Action Plan
May 2026
PREPARED FOR OET STAFF

## Slide 2
CONTEXT
What We've Been Dealing With
4×
Pending queue growth
since 2021
+33%
Applications received growth
same period
283/mo
Capacity needed to clear backlog
vs ~150 processed
58%
FAS share of apps routed
avg 17 days in FCC
The volume of incoming applications does not explain the backlog. Operating under clearance capacity is the primary driver. The team has been asked to absorb more work than the system was designed to handle.
For every 1 day an application spends inside FCC, it spends 2 days with the applicant or at interagency — delays upstream cascade onto staff.

## Slide 3
APPROACH
Three Levers to Get Well
1
More Staff Processing Apps
Staff training is already underway. As engineers come up to speed, throughput increases without any system changes.
UNDERWAY
2
Increase Processing Productivity
Fix the tools that slow staff down — eliminate manual data entry, reduce inquiry interruptions, and automate what the system already knows.
THIS PLAN
3
Reduce Incoming App Volume
Smarter pre-filing guidance and renewal reminders reduce repeat and deficient filings — fewer needless applications in the queue.
THIS PLAN

## Slide 4
THE DATA
What's Causing the Delays?
Are applicant filing habits changing?
No.
App type mix (STA 50%, New 31%, Renewal 17%) and experiment type distributions are stable. Volume isn't the culprit.
Is processing slowing down?
Yes — for New apps.
Median disposal days for New applications have risen since 2024. This correlates with the backlog surge and looks like burden-shifting away from harder cases.
Is a barrage of inquiries hurting throughput?
A factor.
~20% of emails are status questions applicants can't answer themselves — because ELS shows only 'Pending' with no detail. ~15% are website filing failures.
Are applicants filing improperly?
Very likely.
65% of renewal filers are late or lapsed. No automated expiration reminders exist. 50% of apps coded as STAs — needs verification.

## Slide 5
PAIN POINTS
Scored Register: Delay × Urgency
# | Pain Point | Reported By | Systems | Delay | Pain | Score
1 | Receiver parameters manually entered into OFACS | Internal | Web Form, ELS | 10 | 10 | 20
2 | Correspondence manually uploaded from Email | Internal | ZenDesk, Email, ELS | 9 | 10 | 19
3 | Form lacks conditionally mandatory fields | Internal | Web Form | 8 | 9 | 17
4 | ELS → OFACS parameter transfer errors | Internal | ELS, OFACS | 6 | 9 | 15
5 | No coordination status visible to applicant | Both | ELS, Web | 4 | 10 | 14
6 | No auto allocation/incumbent check on form | Internal | External DB, Web | 8 | 5 | 13
7 | Form across multiple pages causes browser failures | Applicant | Web Form | 2 | 10 | 12
8 | Amendments reset interagency coordination | Internal | Web, ELS, OFACS | 4 | 8 | 12
9 | Alternative frequencies proposals | Internal | Web, ELS, OFACS | 4 | 8 | 12
Scores: Red ≥17 (critical) · Amber ≥13 (high) · Green <13 (medium) · Full register includes 24 items

## Slide 6
FIX 1 · HIGH IMPACT, LOW EFFORT
Alert Applicants to Pre-Coordination Requirement at Filing
THE PROBLEM
ATC Pre-Coordination
9.26% of all applications
25-day median delay · Fully preventable
FAA Pre-Coordination
7.18% of all applications
14-day median delay · Fully preventable
Combined: 16.44% of all applications
add 14–25 days each · Fully preventable
THE FIX
When a frequency band in the ATC or aviation allocation table is entered on the form, display a warning:
"This frequency requires FAA/ATC pre-coordination. You must attach a pre-coordination document before submission."
Trigger: static frequency band lookup. No ML, no APIs, no backend changes. A front-end shim can implement this.
Estimated impact: eliminate 14–25 day delays for 16.4% of applications

## Slide 7
FIX 2 · MULTI-ISSUE CONSOLIDATION
Rewrite the Web Form (Not ELS) to Resolve Several Issues
CORES Automation
Applicants Unaware of Incumbents
Add Part 15 Compliance Question
Experiment Type → Drill Down Field
Batch Upload Documents
Applicants Unaware of Interagency Coordination
Alternative Freq/Power Proposals
THE FIX
OET creates a new form aligned with github.com/FCC/design-standards.
New form points to the same ELS fields as the current form. New fields store data in the existing Remarks field to avoid schema changes during migration.
When migration completes, Remarks field provides a backfill script for all applications from now until then.
Estimated impact: Reduce 20–30% of inquiries and reduce interagency coordination time

## Slide 8
NEXT
Items to Investigate
STA Volume Audit
50% of apps are coded as STAs — how many are truly short-term? Many appear to be renewed for years. Conventional licenses (2-year) reduce reprocessing burden versus quarterly STAs.
Possible process: when STA expires, direct applicant to file conventional license + STA renewal in parallel. Grant conventional, dismiss STA.
Website Overhaul
Remove outdated information, add relevant FAQs addressing the most common status and filing questions.
Consider: Experimental Licensee listserv to push FAQs, or periodic webinars on common filing issues.
Renewal Reminder System
65% of renewal filers are late or lapsed. No automated expiration reminders currently exist in ELS.
An automated email 90/60/30 days before expiration is a scored pain point (#10) and could meaningfully reduce late/lapsed renewal volume.

## Slide 9
SUMMARY
Action Plan at a Glance
Action | Systems | Effort | Est. Impact | Status
Pre-coordination alert on web form | Web Form | Low | Eliminate 14–25d delays for 16.4% of apps | To Do
Rewrite web form (new FCC design-standards) | Web Form | Medium | Reduce 20–30% of inquiries | To Do
Add applicant-facing status detail in ELS | ELS, Web | Medium | Reduce ~20% of status-inquiry emails | To Do
Automated renewal/expiration reminders | ELS, Email | Low | Reduce late/lapsed renewal rate from 65% | To Do
Auto-populate OFACS from ELS (no re-entry) | ELS, OFACS | High | Eliminate highest-scored delay source | Investigate
Staff training ramp-up | Operations | Ongoing | Increase raw throughput capacity | Underway
STA → conventional license conversion audit | ELS, Policy | Medium | Reduce reprocessing burden long-term | Investigate
Website FAQ / listserv | Web | Low | Reduce inquiry volume broadly | Investigate

## Slide 10
The workload surge was real.
The analysis is done.
Now we fix it.
This plan targets the highest-impact, most-actionable problems first — starting with fixes that require no backend changes and moving to systemic improvements. The goal is measurable backlog reduction and a better experience for both applicants and the staff processing their requests.
OET · Office of Engineering and Technology · May 2026

## Slide 11
PROCESSING TIME ANALYSIS
Does the Application Itself Predict Disposal Days?
More transmitter sites = slower review?
No.
Sites per application show no meaningful link to disposal days. Median STA closes in 15 days whether it has 1 site or 10.
Pearson r=-0.01 Spearman p=-0.15 n=47,674
More frequencies in the app = slower review?
Slightly.
Small but real upward drift on rank-based comparison; doubling n_freqs adds only a few days at the median. Not a primary driver.
Pearson r=+0.07 Spearman p=+0.12 n=47,674
More total bandwidth requested = slower review?
No.
Tested two ways: emission designator (n=21K) and merged-range spectrum span (n=36K). Neither shows a meaningful link.
Spectrum span: Pearson r=+0.02 Spearman p=-0.05 n=35,790
Federal + Non-Federal frequency mix = slower review?
Yes - for long-form licenses.
Negligible for STAs. But for Program Experimental Licenses, non-federal-only apps close in 37 days vs 69 when the app spans Federal allocations. See next slide.
PEL median: 37 days (NF only) vs 69 days (spans both)
Source: 47,674 granted ELS apps with both receipt and grant dates. Federal/Non-Federal classification uses the FCC US Frequency Allocation Table (Primary entries, 2026-02-13).

## Slide 12
WHERE THE EFFECT SHOWS UP
Federal Frequency Use Doubles PEL Disposal Time
Chart: Median disposal days, by license type
| STA | Construction New (CN) | Program Experimental (PL)
Non-Federal frequencies only | 15 | 38 | 37
Spans Federal + Non-Federal | 16 | 48 | 69
KEY TAKEAWAY
+32 days
Added to median PEL disposal when the application's frequencies span Federal allocations (37 -> 69 days).
WHY IT MATTERS
PELs are the slowest license category (median 69 days vs 15 for STAs). If Federal-frequency review is the bottleneck, targeted coordination support there has higher leverage than broad triage changes.
STA n=21,524 | CN n=4,701 | PL n=4,010 (classifiable subset). Excludes 3,301 transfers/assignments/improperly filed mods where no frequencies were re-listed.

## Slide 13
STATISTICAL DETAIL
How To Read These Numbers
WHAT THE COEFFICIENTS MEAN
Pearson r - linear association between two variables.
Range -1 to +1. r = 0 means no straight-line relationship. Sensitive to outliers and assumes a linear pattern.
Spearman p (rho) - rank-based association.
Same -1..+1 range, but operates on rank order. Robust to outliers; captures any monotonic pattern (linear or curved).
RULE OF THUMB
|r| < 0.10 - effectively no relationship 0.10 - 0.30 - weak (rarely operationally meaningful) 0.30 - 0.50 - moderate, plausibly actionable 0.50+ - strong All four candidate drivers tested below land in the first two buckets corpus-wide.
Factor | Pearson r | Spearman p | n | Verdict
Number of sites | -0.01 | -0.15 | 47,674 | None
Number of frequencies | +0.07 | +0.12 | 47,674 | Weak
Total bandwidth (emission) | +0.04 | +0.08 | 21,372 | None
Spectrum span (range) | +0.02 | -0.05 | 35,790 | None
FEDERAL/NON-FEDERAL GROUPING (CLASSIFIABLE APPS)
Cohort | n | Median days | Mean days
Spans Federal + Non-Federal | 31,688 | 24 | 52
Federal frequencies only | 6,234 | 19 | 39
Non-Federal only | 6,366 | 15 | 31
Methodology: receipt_date and grant_date parsed from canonized fields; processing_days clipped to 0-1825. Bandwidth (emission) parses ITU emission designators (HKMG-coded). Spectrum span merges per-app (start, stop) intervals before summing. Group comparisons exclude 3,301 zero-frequency apps (transfers/assignments/improperly filed mods).

## Slide 14
REPEAT STA ANALYSIS
Are Applicants Cycling STAs Instead of Filing Conventional?
Chart: 
|
Amendments (legitimate) | 11352
Extensions (renewal-like) | 4112
Replacements (cycling) | 3331
AMENDMENTS
60.4% / 11,352
Filed DURING the prior STA's active term. Adds sites, frequencies, or parameters to an ongoing experiment. Considered legitimate.
EXTENSIONS
21.9% / 4,112
Filed within +/-30 days of the prior STA's term_end. Acts as a renewal of the same authorization in new STA form.
REPLACEMENTS
17.7% / 3,331
Filed >30 days after the prior STA expired. Gap-cycles a continuous experiment under repeated 6-month STAs.
CYCLING SIGNAL (Extensions + Replacements)
29% / 7,443 of 25,757 classifiable historical STAs
FORCED-CONVENTIONAL UPPER BOUND
Up to 7,400+ STA filings avoidable historically
Method: STAs grouped by normalized applicant name; chains formed via union-find on overlapping frequency intervals (MHz). Bucket assigned per follow-on STA against most-recent prior STA's term_end. n = 18,795 follow-on STAs across 2,585 chains.

## Slide 15
PENDING QUEUE IMPACT
1 in 5 Pending STAs Is From a Cycling-Pattern Applicant
Chart: Composition of pending and active STAs
| Pending (139) | Active (131)
Cycling-pattern | 28 | 17
Amendment-pattern | 58 | 74
Short chain (<=2) | 14 | 14
Isolated | 39 | 26
IF CYCLING-PATTERN APPLICANTS WERE FORCED TO FILE CONVENTIONAL
139 - 28 = 111
Pending queue drops 20% (28 STA filings averted right now).
TOP CYCLING-PATTERN APPLICANTS
Long histories where Extensions + Replacements dominate
Applicant | STAs | Span | Cycle%
Broadcast Sports International | 291 | 10.6 y | 70%
RF Film, Inc. | 145 | 13.5 y | 79%
3G Wireless, LLC | 140 | 17.8 y | 72%
3G Wireless, LLC (chain 2) | 111 | 8.2 y | 74%
CP Communications | 99 | 12.5 y | 85%
Sportvision | 48 | 19.9 y | 74%
MRTC Motorsport Comms | 47 | 12.1 y | 78%
Goodyear Tire & Rubber | 42 | 23.5 y | 76%
Broad Comm, Inc. | 41 | 15.6 y | 98%
Harris Corporation | 40 | 19.3 y | 70%
'Cycling pattern' = chain of >=3 follow-on STAs where Extensions+Replacements >=50%. Pending = status='Pending'; Active = status='Granted' AND term_end >= today. Top-applicants table shows worst chains by cycle %, not by chain length (excludes amendment-heavy giants like SpaceX, Boeing).